| Городокский район |
| --- |
| Наименование проекта: Внедрение новой модели оказания медицинской помощи на дому сельскому населению Городокского района (9370 человек) |
| 2. Срок реализации проекта: 1 год |
| 3. Организация –заявитель, предлагающая проект: Учреждение здравоохранения «Городокская центральная районная больница» |
| 4. Цели проекта: увеличить долю обследованного населения (до 100%) из общего количества сельского населения Городокского района (9370 человек) путем повышения мобильности фельдшерско-акушерской помощи в сельской местности Городокского района на базе 17 ФАП, 6 ВАОП, 1 БСУ. |
| 5. Задачи, планируемые к выполнению в рамках реализации проекта: 1. проанализировать уровень заболеваемости сельского населения Городокского района по ключевым направлениям за 3 последних года 2. проанализировать потенциальные сопутствующие медицинские услуги и помощь, оказываемые сельскому населению на дому. 3.укрепить транспортную базу ФАП и ВАОП электроскутерами в количестве 26 шт. (24 + 2) 4. провести обучение врачебного состава (30 человек) навыкам вождения на электроскутере, правилам по обращению с электроскутером. 5. провести санпросветработу для сельского населения Городокского района (9370 человек) о мобильных возможностях ФАП и ВАОП по оказанию медицинской помощи и ранней диагностике на дому 6. провести анализ проведенной работы, изучить возможность преемственности новой модели оказания медицинской помощи в других регионах Витебской области |
| 6. Целевая группа: сельское население Городокского района в количестве 9370 человек |
| 7. Краткое описание мероприятий в рамках проекта: 1.1. провести врачебную конференцию на базе Городокской ЦРБ с участием фельдшеров-акушеров ФАП, ВАОП, СУБ для подведения итогов работы за 3 последних года по уровню смертности и профилактике заболеваемости сельского населения Городокского района– отв. координатор проекта, врачебный состав (40 человек) – 2 недели 1.2. провести анализ заболеваемости и смертности сельского населения Городокского района с последующим изучением причин высоких показателей смертности по ключевым направлениям (онкология, БСК, профилактика ЗОЖ) – отв. координатор, врачебный состав (5 человек) – 1 неделя 1.3. провести обучение (повышение квалификации) врачебного персонала по ранней диагностике (выявляемости) по «ключевым» направлениям на базе Медицинского университета – отв. отдел кадров, врачебный персонал – 6 месяцев 2.1. провести врачебную конференцию на базе Городокской ЦРБ с участием фельдшеров-акушеров ФАП, ВАОП, СУБ для анализа потенциальных сопутствующих медицинских услуг, оказываемых на дому сельскому населению Городокского района в текущем году и в последующие годы – отв. координатор проекта, врачебный состав – 2 недели 2.2. провести анкетирование среди сельского населения о потенциальных сопутствующих услугах, оказываемых фельдшером-акушером на дому, с выбором из предложенных вариантов медицинских услуг, а также с возможностью предложения своего варианта, изучение полученных результатов – отв. координатор, врачебный состав, сельские советы, почтовые отделения (отделение, почтальоны), сельское население – 1 месяц. 2.3. анализ потребности в необходимых технических средствах для возможности обследования сельского населения на дому, а также для оказания востребованных (по итогам проведенного анкетирования, по итогам проведенной врачебной конференции) сопутствующих медицинских услуг для сельского населения – отв. бухгалтерия, врачебный состав – 1 месяц 3.1. расчет стоимости инструментальной базы, транспортной базы для обследования сельского населения на дому, расчет рабочего времени фельдшеров-акушеров на ФАП, ВАОП, СУБ, составление графиков плановых выездов фельдшеров-акушеров в домохозяйства на закрепленных территориях – отв. бухгалтерия, врачебный состав – 1 месяц 3.2. проведение процедуры закупки электроскутеров в необходимом количестве – отв.координатор, специалист по закупкам – 2 месяца 3.3. приведение мест хранения и подзарядки электроскутеров в соответствии с условиями хранения – отв.технический персонал, врачебный персонал – 3 месяца 3.4. проведение процедуры закупки средств корпоративной связи с использованием современных информационных технологий, с инсталлированной навигационной системой на основе GPS 4.1. заключение договоров на оказание услуг по обучению вождению фельдшеров-акушеров ФАП, ВАОП, СУБ Городокской ЦРБ на электроскутере – отв. юрисконсульт – 1 месяц 4.2. обучение вождению фельдшеров-акушеров ФАП, ВАОП, СУБ – отв. координатор, врачебный состав – 2 месяца 4.3. обучение работе с навигационной системой фельдшеров-акушеров ФАП, ВАОП, СУБ Городокской ЦРБ (организация курсов на базе ЦРБ) – отв. координатор, врачебный состав – 1 месяц 5.1. закупка полиграфической продукции для оформления технических средств и помещений в соответствии с требованиями грантодателя – отв.координатор, специалист по закупкам – 1 месяц 5.2. закупка МФУ с возможностью цветной лазерной печати (в количестве 1 шт.) для изготовления листовок, буклетов со списком предоставляемых медицинских услуг на дому, визиток с контактными данными фельдшера-акушера и их последующего размещения в местах общественного пользования (ФАП, ВАОП, СУБ, почта, сельский совет, сельские школы), для изготовления бланков для проведения анкетирования сельского населения, для изготовления листовок и буклетов по профилактике НИЗ и ЗОЖ для их последующего распространения среди сельского населения – отв. координатор, специалист по закупкам – 1 месяц. 5.3. изготовление, распространение информационных материалов о предоставляемых медицинских услугах на дому сельскому населению – отв. координатор, врачебный состав – 2 месяца 5.4. размещение информации о предоставляемых медицинских услугах на дому в печатных районных СМИ, на сайте Городокской ЦРБ, а также на сайте районного исполнительного комитета – отв. координатор, технический персонал РИК, редакция ПСМИ – 1 неделя 5.5. привлечение волонтерской помощи для распространения печатных информационных материалов о предоставляемых медицинских услугах на дому, а также контактов фельдшеров-акушеров – отв. координатор, врачебный персонал, СМИ – 3 недели 5.6. информирование сельского населения Городокского района при проведении «выездных приемов» представителей местной исполнительной власти, выступление в сельских советах и сельских школах – отв. координатор, РИК – 1 месяц 6. 1. проведение опроса среди населения сельского района по итогам предоставления медицинских услуг фельдшерами-акушерами на дому за текущий год – отв. координатор, врачебный состав, сельские советы, почтовые отделения (отделение, почтальоны), сельское население – 1 месяц 6.2. проведение итоговой конференции по результатам опроса сельского населения, для подведения итогов работы за прошедший год по уровню смертности и профилактике заболеваемости сельского населения Городокского района – отв. координатор, врачебный состав – 2 недели 6.3. корректировка качества и спектра оказываемых медицинских услуг на дому сельскому населению фельдшерами-акушерами в будущем году – отв. координатор, врачебный состав. 6.4. последующая работа по разработке и распространению информационных печатных материалов по пропаганде ЗОЖ, профилактике НИЗ – отв. координатор, врачебный состав – последующие годы. |
| 8. Общий объем финансирования (в евро): |
| Источник финансирования | Объем финансирования (в евро) |
| Средства донора | 107 000 |
| Софинансирование | 28 000 |
| 8. Место реализации проекта (область/район, город): Витебская область, Городокский район, г.Городок, ул. Соболевского, 66 |
| 9. Контактное лицо: В.В. Самсонов, главный врач, +375 2139 52234, gorodok_tmo@vitebsk.by М.В. Виноградова, координатор проекта, +37529 5925132, vinogradovamaria85@gmail.com |

Будем рады сотрудничеству!

| Gorodok district |
| --- |
| 1. Project name: Introduction of a new model of providing medical care at home to the rural population of Gorodok district (9370 people) |
| 2. Project implementation period: 1 year |
| 3. The applicant, the proposed project: health care Institution "Haradok Central District Hospital» |
| 4. Project goals: to increase the share of the surveyed population (up to 100%) from the total rural population of Gorodok district (9370 people) by increasing the mobility of paramedic and obstetric care in rural areas of Gorodok district on the basis of 17 paramedic and midwifery centers, 6 general practice outpatient clinics, 1 hospital nursing care. |
| 5. Tasks planned for implementation within the framework of the project: 1. to analyze the level of morbidity of the rural population of Gorodok district in important directions for last 3 years. 2. to analyze potential related health services and assistance provided to rural populations at home. 3. to strengthen the transport base of the paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care with electric scooters in the amount of 26 PCs. (24 + 2) 4. to conduct training of medical staff (30 people) in driving skills on an electric scooter, rules for handling an electric scooter. 5. to conduct an information work for the rural population of Gorodok district (9370 people) about the mobile capabilities of paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care to provide medical care and early diagnosis at home 6. to analyze the work done, to study the possibility of continuity of the new model of medical care in other districts of the Vitebsk region |
| 6. Target group: rural population of Gorodok district in the number of 9370 people |
| 7. Brief description of the project activities: 1.1. to hold a medical conference on the basis of Gorodok CDH with the participation of paramedics-midwives paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care to summarize the work for last years on the level of mortality and prevention of morbidity of the rural population of Gorodok district - project coordinator, medical staff (40 people) - 2 weeks 1.2. to analyze the morbidity and mortality of the rural population of Gorodok district, followed by the study of the causes of high mortality rates in important direction (oncology, diseases of the circulatory system, prevention of healthy lifestyle) - project coordinator, medical staff (5 people) - 1 week 1.3. to conduct training (advanced training) of medical personnel on early diagnosis (detection) in important directions on the basis of the Medical University - HR Department, medical staff – 6 months 2.1. hold a medical conference on the basis of Gorodok CDH with the participation of paramedics-midwives paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care to analyze the potential accompanying medical services provided at home to the rural population of Gorodok district in current year and subsequent years - project coordinator, medical staff – 2 weeks 2.2. to conduct a survey among the rural population about the potential related services provided by a paramedic-midwife at home, with a choice of the proposed options for medical services, as well as with the possibility of offering your own option, study the results - coordinator, medical staff, village councils, post offices (Department, postmen), rural population – 1 month. 2.3. analysis of the need for the necessary technical means to be able to survey the rural population at home, as well as to provide in-demand (based on the results of a survey, based on the results of a medical conference) related medical services for the rural population - accounting, medical staff – 1 month 3.1. calculation of the cost of the tool base, transport base for the diagnosing of the rural population at home, calculation of the working time of paramedics-midwives, drawing up schedules of planned visits of paramedics-midwives to households in the assigned territories - accounting, medical staff – 1 month 3.2. conducting the procedure for purchasing electric scooters in the required quantity - coordinator, procurement specialist – 2 months 3.3. bringing the places of storage and charging of electric scooters in accordance with the storage conditions - technical staff, medical staff – 3 months 3.4. conducting the procedure for purchasing corporate communications equipment using modern information technologies, with an installed GPS-based navigation system 4.1. conclusion of contracts for the provision of driving training for paramedics-midwives paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care of the Gorodok CDH on an electric scooter - legal adviser – 1 month 4.2. driving training for paramedics-midwives paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care - coordinator, medical staff – 2 months 4.3. training to work with the navigation system of paramedics-midwives paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care of the Gorodok CDH (organization of courses on the basis of CDH) - coordinator, medical staff – 1 month 5.1. purchase of printing products for the design of technical facilities and premises in accordance with the requirements of the grantee - coordinator, procurement specialist – 1 month 5.2. purchase of MFPs with the possibility of color laser printing (in the amount of 1 PC.) for the production of leaflets, booklets with a list of medical services provided at home, business cards with the contact details of a paramedic-obstetrician and their subsequent placement in public areas (paramedic and midwifery centers and general practice outpatient clinics, hospital nursing care, post office, village Council, rural schools), for the production of forms for conducting surveys of the rural population, for the production of leaflets and booklets on the prevention of non-infectious diseases and healthy lifestyle for their subsequent distribution to the rural population – coordinator, procurement specialist – 1 month. 5.3. production and distribution of information materials about the medical services provided at home to the rural population - coordinator, medical staff – 2 months 5.4. placement of information about provided medical services at home in regional printed media, on the website Gorodok CDH, and a District Executive Committee – coordinator, technical staff, the editors of media – 1 week 5.5. attracting volunteer help to distribute printed information materials about medical services provided at home, as well as contacts of paramedics-midwives -coordinator, medical staff, media – 3 weeks 5.6. informing the rural population of Gorodok district during "field receptions" of representatives of local Executive authorities, speaking in village councils and rural schools - coordinator, District Executive Committee – 1 month 6. 1. conducting a survey among the population of a rural district based on the results of providing medical services by paramedics-midwives at home in current year - coordinator, medical staff, village councils, post offices (Department, postmen), rural population – 1 month 6.2. holding a final conference on the results of a survey of the rural population, to summarize the results of work for current year according to the level of mortality and prevention of morbidity of the rural population of the Gorodok district - coordinator, medical staff - 2 weeks 6.3. adjustment of the quality and range of medical services provided at home to the rural population by paramedics-midwives for next year - coordinator, medical staff. 6.4. follow-up work on the development and dissemination of printed information materials on the promotion of healthy lifestyle, prevention of non-infectious diseases - coordinator, medical staff-the following years. |
| 8. The total amount of funding (in euros): |
| Source of financing | Amount of financing (in euro) |
| Donor funds | 107 000 |
| Co-financing | 28 000 |
| 8. Project location (region/district, city): Vitebsk region, Gorodoksky district, Gorodok, Sobolevsky str., 66 |
| 9. Contact person: Valery Samsonov, chief medical officer, +375 2139 52234, gorodok_tmo@vitebsk.by Maria Vinogradova, project coordinator, +37529 5925132, vinogradovamaria85@gmail.com |

We will be happy to cooperate!